## Project Tracker
Project Title | Project Type | Project Status | Project Priority Level | Contribution Type | Feasibility Undertaken? | Alternative / Match Funding Identified? | Statutory undertaker remit? | Linked to SA? | Estimated / Agreed Cost | Funding Secured | Lead Organisation | 2015-2020 | 2021-2025 | 2026-2031 | Notes | Appropriate for CIL?
M5 J9 to M6 J11a | Transport | Completed | Critical | Service provider | Y | Y | N | N | 192000000 | 192000000 | Highways England | Construction | Operational |  | Upgrade motorway to a smart motorway increasing capacity during peak times and controlling vehicle flows | No
M5 J9 | Transport | Feasibility | Critical | Service provider | Y | Y | N | Ashchurch | 249000000 | 0 | Highways England |  | Construction | Operational | In January 2020, GCC applied to the DfT for Large Local Majors funding to finance the scheme. Extended junction to accommodate new off-line A46 (Ashchurch). Funded partly through the A46 Ashchurch Scheme. | No
M5 J10 | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N | N | 220000000 | 220000000 | Homes England / GCC Transport |  | Construction | Operational | Housing Infrastructure Fund monies secured for £219m from Homes England in March 2019. High capacity upgrade of M5 J10 junction providing an ‘All Movements’ junction including three lanes on slip roads and circulatory lanes on the roundabout to accommodate the associated Cyber Park access road / A4019 junction (Scheme ref 28). This will be a high capacity signal controlled junction, with a separate left turn slip road from M5J10 northbound off-slip onto Cyber Park link road (southbound). New signals on A4019 westbound entry to upgrade motorway junction. | No
M5 J11 | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | Highways England |  | Construction | Operational | Signalise South Bound off-slip. North Bound off slip extra lane. Strategic scheme priority in the LTP3 | No
M5 11a | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | Highways England |  | Construction | Operational | Optimise junction operation with improved signing and lining and area wide reassignment. Strategic scheme priority in the LTP3 | No
M5 J12 | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N | N | 12500000 | 0 | Highways England |  | Construction | Operational | Upgrade to junction to include 2 lane wide off and on slips. Strategic scheme priority in the LTP3 | No
A417 Missing Link | Transport | Planning | Critical | Capital Ex | Y | Y | N | N | £250m-£500m | Yes | Highways England | Construction | Construction | Operational | Identified in Highways England Road Investment Strategy. Development Consent Order application to be submitted late 2020.
Gloucester South West Bypass (A430 Llanthony Rd and St. Ann Way improvement) | Transport | Construction | Critical | Capital Ex | Y | Y | N | N | 7450000 | 7450000 | Gfirst LEP / GCC Transport | Construction | Operational |  | Project within the Countywide revenue highway project delivery priorities (2015-2031) and the Gloucestershire Economic Growth Capital Investment Pipeline (CIP). The scheme is partly funded by the Gloucestershire Growth Deal, where £2m of funding has been invested by GFirst LEP. lanning consent was granted in April 2019. GA condition of the money being awarded is that the Llanthony Road scheme has to be complete by 2021.
London Road / Denmark Road Junction improvement | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N | N | Unknown | 0 | GCC Transport |  |  |  | Project within the Countywide revenue highway project delivery priorities (2015-2031).
A40/A48 Highnam Roundabout | Transport | Completed | Critical | Ad-hoc funding opportunities | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | Signalise roundabout – MOVA signals. Works copleted in September 2018. | Yes
A40 Over Roundabout | Transport | Completed | Critical | Ad-hoc funding opportunities | Y | Y | N | N | 2500000 | 2500000 | GCC Transport | Construction | Operational |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings | N/A
A40 Longford Roundabout | Transport | Construction | Critical | Ad-hoc funding opportunities | Y | N | N |  | 3000000 | 3000000 | GCC Transport | Operational |  |  | Existing A40 / A38 Longford junction changed from a roundabout to a signalised crossroads. Junction arrangement designed to complement the introduction of Longford Bypass. Turn from A40 east to A38 north not allowed. Bus priority – traffic signals will be used to facilitate north / south movements. Construction due to start in May 2020. | Yes
A40(T) Innsworth Gateway Roundabout | Transport | Planning | Critical | Developer contributions | Y | Y | N |  | 3000000 | 1500000 | TBC / G First LEP | Construction | Operational |  | New signalised junction on A40 between Longford and Elmbridge Court roundabouts | Yes
A4019/ B4634 Old Gloucester Rd | Transport | Feasibility | Critical | Developer contributions | Y | N | N | N | Unknown | 0 | GCC Transport |  | Construction | Operational | Revised A4019 traffic signals at site access junction identified in the draft LTP3 | Yes
New junction on A38 | Transport | Feasibility | Critical | Developer contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | New priority junction on A38 giving priority to new highway link accessing to new junction on A40 (scheme 17) | Yes
A38-A40 highway link | Transport | Feasibility | Critical | Developer contributions | Y | N | N |  | 7500000 | 0 | GCC Transport |  |  |  | New 50 mph highway link, joining upgraded junctions on A40 and A38 through development site | Yes
A38 Tewkesbury Road | Transport | Feasibility | Critical | Developer contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | A38 Tewkesbury Road to be downgraded between A40/A38 Longford signalised crossroads and new A38/Twigworth junction to 20mph, and encourage as a sustainable travel corridor. Access from A38 north is restricted to one lane entry to crossroads, A40 west to A38 north - right hand turn banned with alternative route via A40 / A38 Link Road. | Yes
A38 Tewkesbury Road | Transport | Feasibility | Critical | Developer contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Upgrade A38 Tewkesbury Rd / Down Hatherley Lane junction, to include a dedicated right turn from A38 south. | Yes
A40 Elmbridge Court Roundabout | Transport | Completed | Critical | Local Growth Fund | Y | Y | N | N | 12500000 | 12500000 | GCC Transport | Operational |  |  | Remove B4063 Cheltenham Rd East approach arm from the junction and remove Business Park arm. | No
A417 / Delta Way ‘Zoons’ Roundabout | Transport | Feasibility | Critical | Local Growth Fund | Y | Y | N |  | 3000000 | 3000000 | GCC Transport |  |  |  | Junction Improvement: Removing the existing left turn slip from Delta Way (Brockworth) to C&G Roundabout, and signalising the A417 approach (from Cirencester) and the opposing roundabout circulatory movement. | No
A417 Brockworth Bypass | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Signalising the westbound and eastbound ‘Off-slips’. | Yes
A40 / A417 C&G roundabout | Transport | Completed | Critical | Ad-hoc funding opportunities | Y | Y | N | N Brockworth | 3000000 | 3000000 | GCC Transport | Construction | Operational |  | A40 / A417 C&G roundabout –Capacity Improvement on 2014 Pinch Point Scheme, by provision of a ‘free left turn lane’ from the A40 Barnwood Link approach arm to A417 Barnwood Bypass, and from A417 Corinium Avenue approach arm to A40 Barnwood Link. Improvements part-funded through s.106 agreement for North Brockworth (£200,000) | N/A
A38 / Walls roundabout | Transport | Completed | Critical | Ad-hoc funding opportunities | Y | Y | N | N | 3000000 | 3000000 | GCC Transport | Construction | Operational |  | Capacity Improvement on 2014 Pinch Point Scheme, by providing 3 lane circulatory on the roundabout between Barnwood Rd / A38 Eastern Avenue approaches. | N/A
A38 / A4173 St. Barnabas roundabout | Transport | Feasibility | Critical | Developer contributions | Y | N | N |  | 7500000 | 1000000 | GCC Transport | Construction | Operational |  | Remove roundabout and signalising junction(with removal of Reservoir Rd approach arm) Part-funded by Gfirst LEP | Yes
A38 / A430 / B4008 Cole Avenue | Transport | Feasibility | Critical | Local Growth Fund | Y | Y | N |  | 7500000 | 7500000 | GCC Transport |  |  |  | A38 / A430 / B4008 Cole Avenue Junction - Grade separation to allow straight through movement of north / south traffic on A38 Southern Connector/A430 corridor | No
A430/A417 Castlemeads | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings | Yes
A38 Cross Keys Roundabouts | Transport | Completed | Critical | Ad-hoc funding opportunities | Y | Y | N |  | 3850000 | 3850000 | GCC Transport | Construction | Operational |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings. Construction completed in October 2019. | No
New A40 Access/Improvements | Transport | Feasibility | Critical | Developer delivery | Y | Y | N | S Churchdown | Cost to Developer | N/A | Developer | Construction | Operational |  |  | No
Tewkesbury Road improvements | Transport | Feasibility | Critical | s.106 | Y | Y | N | NW Chelt | 4500000 | 4500000 | GCC Transport |  | Construction | Operational |  | No
A38 Coombe Hill | Transport | Feasibility | Critical | Ad-hoc funding opportunities | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Optimise signals | Yes
New junction west of M5 J10 | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 22500000 | 0 | GCC Transport |  |  |  | New 50 mph dual carriageway two-lane link road, providing free-flow access from A4019 / M5J10 to West of Cheltenham site only. | Yes
West of M5 J10 | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | Major/Minor Priority Junction on new 50 mph dual carriageway two-lane link road, with Minor junction arm for West of Cheltenham residential site access only. | Yes
West of M5 J10 | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 7500000 | 0 | GCC Transport |  |  |  | Change to highway priorities west of M5J10, with a new Major/Minor Priority Junction, with A4019 (West) as Minor junction arm. | Yes
A4019 / A4013 Kingsditch | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | A4019 / A4013 Kingsditch (Centrum Park) Roundabout – replacing existing roundabout with traffic signals, | Yes
West of B4634 Old Gloucester Road | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | New A4019 traffic signals site access junction, west of B4634 Old Gloucester Rd | Yes
A4019 / B4634 Gallagher Retail Park | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | Revised A4019 traffic signals site access junction at B4634 Old Gloucester Rd / Gallagher Retail Park | Yes
A4019 Tewkesbury Road | Transport | Feasibility | Critical | Ad-hoc funding opprtunities | Y | N | N |  | 7500000 | 0 | GCC Transport |  |  |  | Upgrade signals to SCOOT operation to optimise signal timings with bus priority along A4019 corridor junctions including: B4634 Old Gloucester Rd/A4019 Junction Hayden Road/A4019/Manor Road Junction A4019 / Elm Street Junction B4633 Gloucester Rd / A4019 /Townsend Street | Yes
Withybridge Lane | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Close access onto A4019 | Yes
A435 / Hyde Lane / Southam Lane Signalised Junction | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Signalised Junction -Upgraded to provide additional straight ahead lanes on all junction approaches | Yes
A435/ Stoke Road and A435 / Finlay Way Roundabouts | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Capacity Improvements by approach arm widening | Yes
A435/GE Aviation Roundabout | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | Capacity Improvements by increasing the number of circulatory lanes to 2, and the A435 south bound exit to two lanes | Yes
A435 / Racecourse Roundabout | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | Capacity Improvements by approach arm widening | Yes
Arle Court Park and Ride | Transport | Planning | Critical | Local Growth Fund | Y | Y | N | W. Chelt | 7500000 | 7500000 | Bus provider | Construction | Operational |  | Expansion of existing Arle Court P&R parking facilities (100% Increase in Capacity), and new walking and cycling improvements to link P&R site with the new West of Cheltenham Employment site. £1m of funding from Stagecoach West. | No
Arle Court Park and Ride / A40 Arle Court Roundabout | Transport | Completed | Critical | Local Growth Fund | Y | Y | N | W. Chelt | 3000000 | 3000000 | GCC Transport | Operational |  |  | New signalised junction on the A40 to the west of Arle Court roundabout to provide access into Park and Ride site only. With left turn out and right turn in only. This will not allow through traffic into Hatherley Lane. | N/A
West Cheltenham Transport Improvement Scheme | Transport | Construction | Critical | Local Growth Fund | Y | Y | N | W. Chelt | 8500000 | 8500000 | GCC Transport | Construction | Operational |  | Extra lanes at Benhall Roundabout and Telstar Way, and a new cycling and walking route connecting Cheltenham Railway Station to Arle Court Roundabout. Funded by Gfirst LEP.
Leckhampton Lane | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | Upgrade A46 / Leckhampton Lane priority junction, to include a dedicated right turn from A46 south into Leckhampton Lane. | Yes
A46 / Moorend Park Road | Transport | Feasibility | Critical | Developer Contributions | Y | N | N |  | 3000000 | 0 | GCC Transport |  |  |  | A46 Shurdington Road northbound approach to Moorend Park Road – additional highway space for right turning traffic by providing a longer stacking lane. | Yes
Badgeworth Lane | Transport | Feasibility | Essential | Ad-hoc funding opprtunities | Y | N | N |  | 1000000 | 0 | GCC Transport |  |  |  | A46 / Badgeworth Lane priority Junction – Signalisation of junction to provide improved access to/from Badgeworth. | Yes
North West Cheltenham Site Enabling Works | Transport | Feasibility | Essential | Ad-hoc funding opprtunities | Y | Y | N | NW Chelt | 17000000 | 17000000 | GCC Transport |  |  |  | New A4019 Tewkesbury Road accesses, new access from Manor Road and Public Transport only access via Quat Goose Lane. The S.278 agreement between the highways authority and the developer sets out a package in region of £17m. | No
A46 Ashchurch | Transport | Pre-application | Essential | Highways England Funding | Y | Y | N | N | 70000000 | 70000000 | GCC Transport |  |  |  | New dual carriageway bypass linking Teddington Hands roundabout with M5 Junction 9 and associated changes to junctions. Based on the Department for Transport’s 1993 alignment. Identified in draft LTP3 (2015-2041) | No
Grange Road / Hardwicke Bank Road | Transport | Feasibility | Essential | Local Growth Fund | Y | Y | N | N | 7500000 | 7500000 | GCC Transport |  |  |  | Close Railway Level Crossing, and replace with new bridge linking Grange Road with Hardwicke Bank Road | No
Alexandra Way / A46 | Transport | Feasibility | Essential | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | GCC Transport |  |  |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings | Yes
Fiddington Lane / A46 | Transport | Feasibility | Essential | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | GCC Transport |  |  |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings | Yes
Northway Lane / A46 | Transport | Feasibility | Essential | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | GCC Transport |  |  |  | Upgrade signals to MOVA or SCOOT operation to optimise signal timings | Yes
Shannon Way | Transport | Feasibility | Essential | Local Growth Fund | Y | Y | N | N | 3000000 | 3000000 | GCC Transport |  |  |  | Improvement to the A438/Shannon Way traffic signal junction to provide an additional eastbound exit lane from the junction to M5J9; separate left turn lane from A438 (west) to Shannon Way, with two straight ahead lanes eastbound. Upgrade signals to MOVA or SCOOT operation to optimise signal timings | Yes
A438/A38 Tewkesbury Bypass | Transport | Feasibility | Essential | Ad-hoc funding opportunities | Y | N | N | N | 1000000 | 0 | GCC Transport |  |  |  | Upgrade signals to MOVA to optimise signal timings | No
B4063 Staverton Crossroads | Transport | Feasibility | Essential | Ad-hoc funding opportunities | Y | N | N | N | 1600000 | 0 | GCC Transport |  |  |  | Modelling undertaken in 2019.
Elmbridge Court Interchange | Transport | Feasibility | Essential | Ad-hoc funding opportunities | N | N | N | N |  |  | GCC Transport
Abbeymead/Metz Way | Transport | Delivery | Essential | Ad-hoc funding opportunities | Y | Y | N | N | 500000 | 500000 | GCC Transport |  |  |  | Identified in the Gloucestershire Economic Growth Capital Investment Pipeline (CIP).
North West Cheltenham all-through school | Education | Planning | Critical | Developer delivery | Y | Y | N | NW Chelt | Cost to Developer | N/A | Developer / GCC Education |  | Construction | Operational |  | No
97/98 Bus Diversion, Innsworth | Transport | Feasibility | Essential | Service provider | N | Y | N | Innsworth | Cost to Service Provider | N/A | Bus provider |  | Operational |  |  | No
Bus Diversion, S. Churchdown | Transport | Feasibility | Essential | Service provider | N | Y | N | S Churchdown | Cost to Service Provider | N/A | Bus provider |  | Operational |  |  | No
Two-form primary school, Innsworth | Education | Feasibility | Essential | Developer delivery | Y | Y | N | Innsworth | Cost to Developer | N/A | Developer / GCC Education | Construction | Operational |  |  | No
Healthcare and Community Hub, Churchdown | Healthcare | Feasibility | Essential | Land/Property | Y | Y | N | S Churchdown | Cost to Service Provider | N/A | Developer / NHS | Construction | Operational |  |  | Yes
New GP Surgery, Innsworth | Healthcare | Feasibility | Essential | Land/Property | Y | Y | N | Innsworth | Cost to Developer | N/A | Developer / NHS | Construction | Operational |  |  | No
New 1.5 FE primary school, Brockworth | Education | Feasibility | Essential | s.106 | Y | Y | N | N Brockworth | 3893085 | 3893085 | Developer / GCC Education | Construction | Operational |  | Has this been delivered? | No
Secondary School contribution | Education | Feasibility | Essential | s.106 | Y | Y | N | N Brockworth | 2743200 | 2743200 | Developer / GCC Education | Construction | Operational |  | Has this been delivered? | No
Gloucestershire STEM Centre upgrades | Education | Feasibility | Essential | Service provider | Y | Y | N | N | 2096000 | 2096000 | GCC education | Construction | Operational
New GP Surgery, N. Brockworth | Healthcare | Feasibility | Essential | Land/Property | Y | Y | N | N Brockworth | Cost to Developer | N/A | Developer / NHS | Construction | Operational |  | Identified in PCIP. Development of single facility to replace existing surgery sites for up to 25,000 patients. Business case in development. | No
Park & Ride, NW Cheltenham | Transport | Feasibility | Essential | Service provider | N | N | N | NW Chelt | Unknown | 0 | GCC Transport |  |  |  |  | Yes
Public Transport Hub | Transport | Feasibility | Essential | Developer delivery | Y | Y | N | NW Chelt | Cost to Developer | N/A | Developer |  | Construction | Operational |  | No
Bus Improvements, Ashchurch | Transport | Feasibility | Essential | Developer delivery | Y | Y | N | Ashchurch | Cost to Service Provider | N/A | Bus provider |  |  |  | This should have been delivered? | Yes
Winneycroft new pumping station | Water /Flood Risk | Feasibility | Essential | Service provider | Y | Y | Severn-Trent Water | Winneycroft | Cost to Service Provider | N/A | Wastewater provider |  |  |  | New pumping station needed to increase capacity in relation to additional development at Winneycroft | No
North West Cheltenham GP and Dental Surgery | Healthcare | Planning | Essential | Developer delivery | Y | Y | N | NW Chelt | Cost to Developer | N/A | Developer |  | Construction | Operational | Identified in PCIP. Delivery route and solution to be agreed. | No
Cycling link to Cheltenham, Bishops Cleeve and Tewkesbury | Transport | Feasibility | Desirable | Ad-hoc funding opportunities | Y | Y | N | NW Chelt | 2750000 | 2000000 | Gloucestershire County Council |  | Construction | Operational | Planning obligations received from developer. | No
Community Centre, NW Chelt | Community | Feasibility | Desirable | Land/Property | Y | Y | N | NW Chelt | Cost to Developer | N/A | Developer |  | Construction | Operational |  | No
Community Centre, Winneycroft | Community | Feasibility | Desirable | Developer delivery | Y | Y | N | Winneycroft | Cost to Developer | N/A | Developer |  |  |  |  | No
Ashchurch for Tewkesbury Rail Improvements | Transport | Feasibility | Desirable | Ad-hoc funding opportunities | N | N | N | N | Unknown | 0 | GCC Transport |  | Construction | Operational | Rail junction and capacity improvements (Dynamic Loops) to Birmingham - Bristol Mainline near Ashchurch to enable more trains to operate and more stopping services, including possible new stations
Gloucester Railway Station improvements | Transport | Feasibility | Desirable | Local Growth Fund | Y | Y | N | N | 9000000 | Local Growth Fund | LEP / Gloucester City Council / Network Rail |  | Construction | Operational | Identified within the Gfirst LEP SEP and the Gloucestershire Economic Growth Capital Investment Pipeline (CIP). Business Case for Gfirst LEP in development | Yes
Gloucester Railway Mainline Platforms | Transport | Feasibility | Desirable | Service provider | Y | Y | N | N | £50-100m | 0 | Network Rail |  | Construction
Cheltenham Railway Station improvements | Transport | Construction | Desirable | Local Growth Fund | Y | Y | N | N | 1497000 | Local Growth Fund | LEP / Service Provider | Construction | Operational |  | Commenced on site this includes the forecourt, additional car parking, cycle facilities and now working on the Honeyborne Line extension that has gretaer complexities due to land within Network Rail control. Target for all to be delivered by end of Franchise March 2020. | Yes
Gloucester Towpath Improvements | Transport | Planning | Desirable | Ad-hoc funding opportunities | Y | Y | N | N | 433736 | European Regional Development Fund | Gloucestershire County Council | Construction | Operational |  | The project aims to improve the quality of the towpath by completely resurfacing it
Anson Park, Gloucester Airport | Business | Feasibility | Desirable | Local Growth Fund | Y | Y | N | N | 1900000 | Local Growth Fund | LEP |  | Construction | Operational | Provision of a new access road, associated infrastructure and a new junction onto the B4063 Cheltenham Road East in order to bring forward a further 4.0 Ha of employment land on the airfield. £1.885m of Growth funds allocated in F/Y 20-21. Identified within the Gfirst LEP SEP | Yes
Leckhampton School | Education | Planning | Essential | Developer funded | Y | Y | N | Leckhampton | Unknown | Developer contributions | GCC Education | Construction | Operational |  | New 900 Place School sponsored by Balcarras trust in Charlton Kings. Planning decision due May 2020
Innsworth Infant School Expansion | Education | Completed | Essential | Service provider | Y | Y | N | Innsworth | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | One additional classroom to support the school increasing from a Pupil Admission Number (PAN) of 50 to 60 from Sept 2019 | Yes
Barnwood Park | Education | Completed | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | Barnwood Park Arts College will expand by 1 form of entry which is equivalent to an additional class of 30 pupils from September 2019. | Yes
Finlay Community School | Education | Completed | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | Work completed in summer 2019 at Finlay Community School to expand the school by 1 form of entry, which will equal 210 pupils overall. | Yes
Churchdown Junior School | Education | Completed | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | Expansion of the school to build a new classroom to cater for an additional 30 new reception places from September 2019. | Yes
Mill Lane School, Brockworth | Education | Planning | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | GCC Education | Service Provider |  | Construction | Operational | New SEMH school. Due to open in 2022, and will provide 75 places for girls and boys.
Milestone School | Education | Planning | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | New accommodation for a dedicated facility for children and young people with complex difficulties | Yes
Clearwater Primary School | Education | Construction | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | The Department for Education are progressing with the delivery of the school building with a view to getting the new school building open and operational in September 2020. | Yes
New Brockworth Primary Academy | Education | Completed | Essential | Service provider | Y | Y | N | N | Cost to Service Provider | N/A | Service Provider | Construction | Operational |  | Building works started in February 2019 and completed in September 2019. | Yes
Cheltenham Cyber Park | Business | Planning | Desirable | Local Growth Fund | Y | Y | N | West Cheltenham | 600000000 | Central Govt, CBC and LEP funded | West Cheltenham Consortium |  | Construction | Operational | 45ha site which will focus upon specialist cyber security businesses, technology and research. The proposed development would provide accommodation for start-ups, SME’s and large corporations. The whole development would measure 135 ha, of which the Cyber Park would measure 45ha and provide 7,000 jobs. | No
High Street Public Realm Enhancement, Cheltenham | Public Realm | Complete (Phase 1), further Phases in Feasibility | Desirable | Service provider | Y | Y | N | N | 7500000 | European Structural and Investment Fund / GCC | GCC Transport / CBC | Construction | Operational |  | Public realm improvement between Rodney Road and Cambray Road. Funded in part by ESIF. Phase 1 delivered. Feasibility underway for further phases with estimated costs of approx. £6.5m. £1m funding contribution agreed with GCC. CBC have agreed with senior officer to set out a clear business case for future phases. | No
Kings Quarter Regeneration | Public Realm | Planning | Desirable | Ad-hoc funding opportunities | Y | N | N | N | 1100000 | 0 | GCC / Homes England |  | Construction | Operational | Identified in the Gloucestershire Economic Growth Capital Investment Pipeline (CIP).
Blackfriars Regeneration | Public Realm / Highways | Delivery | Desirable | Local Growth Fund | Y | Y | N | N | 4130000 | Local Growth Fund | Gloucester City Council |  | Construction | Operational | Gloucester City Council have been working in partnership with others to create a Local Development Order for the regeneration of Blackfriars. Gloucester City Council acquired a grant of £4.13 million from central government and GFirst LEP Gloucestershire Growth Deal 2015-2021. The Local Development Order was approved on 7 March 2019. Phase 2 of Student development has planning permission. | No
Tewkesbury Town Centre Masterplan | Public Realm | Feasibility | Desirable | Ad-hoc funding opportunities | N | N | N | N | 5000000 | 0 | TBC |  | Construction | Operational | Adopted SPD supports regeneration of town centre. Includes a bid to the High Street fund in March 2019.
Gloucester Bus Station | Transport | Completed | Essential | Service provider | Y | Y | N | N | 7500000 | 7500000 | GCC Transport / Service Provider | Construction | Operational |  | Bus station construction progressed in August 2017 – Kier and will cost approximately £7.5 million. The development will provide 12no. bus bays and a glass frontage. The project has been delivered. | N/A
Cheltenham GP Surgery Consolidation | Healthcare | Construction | Essential | Service provider | Y | Y | N | N | Unknown | Unknown | GCCG / Service Provider | Construction | Operational |  | Replace up to5 practices with 1 or 2 new surgery sites (Berkeley Place, Crescent Bakery and Royal Crescent). Due to open by New Year 2021. | Yes
Primary Care Hub Gloucester | Healthcare | Planning | Essential | Service provider | Y | Y | N | N | Unknown | Unknown | GCCG / Service Provider | Construction | Operational |  | Gloucester City Health and Gloucester Health Access Centre co-locating into one Primary Care Hub at the Quayside, Gloucester City Centre. Due to open by 2021.
Rikenel Replacement Surgery, Gloucester | Healthcare | Feasibility | Essential | Service provider | N | Y | N | N | Unknown | Unknown | GCCG / Service Provider |  | Construction | Operational | GCCG seek to replace the existing Rikenel building with purpose-built facility | Yes
Bishop's Cleeve Flood Alleviation Scheme | Water /Flood Risk | Feasibility | Essential | s.106 | Y | N | N | N | 220000 | 220000 | Gloucester City Council |  | Construction | Operational | This is a Gloucestershire County Council led scheme to reduce surface water flooding to properties in the Bishops Cleeve area in the Borough of Tewkesbury. Gloucestershire County Council are compiling information needed for an Outline Business Case and conducting a gap-analysis to identify which areas need support from the Programme Delivery Unit. | No
Twyver Natural Flood Management Project | Water /Flood Risk | Feasibility | Desirable | Capital Ex. | Y | Y | N | N | 50000 | 50000 | Defra / Gloucester City Council | Construction | Operational |  | 10 leaky dam structures have been installed at Kites Hill Nature Reserve in partnership with the World Land Trust. Livestock fencing at the Reserve has been programmed for next year. The University of Gloucestershire are carrying out monitoring of watercourses at Kites Hill where work is programmed for 2019 | No
Twyver SuDs and flood risk management | Water /Flood Risk | Construction | Essential | Service provider | Y | Y | N | N | 1285000 | 50000 | Environment Agency | Construction | Operational |  | The Environment Agency is working with partners to deliver a number of inter-linked projects on the Sud Brook and River Twyver by 2021 to reduce flood risk to circa 370 dwellings. Modelling being undertaken with start proposed in March 2019 | No
Epney Kiosk Renovation | Water /Flood Risk | Design | Essential | Service provider | Y | Y | N | N | 50000 | 50000 | Environment Agency | Construction | Operational |  | The Epney river level recorder provides flood warning levels in the tidal reach of the River Severn below Gloucester. The existing site has reached the end of its economic life, and maintenance and repair costs are rapidly rising. The existing structure is to be removed including all in-river structures. A smaller installation using modern level measurement sensors is to be installed on the flood wall. | No
Podsmead Playing Field Sports Complex SuDS | Water /Flood Risk | Feasibility | Desirable | s.106 / Service provider | Y | Y | N | N | 156700 | 156700 | Gloucestershire County Council |  | Construction | Operational | This is a Gloucestershire County Council-led potential scheme to reduce surface water flooding to properties within the Podsmead area of Gloucester. The current proposal is to install a surface water attenuation feature within the Black Ditch Field. | No
Whaddon Flood Alleviation Scheme, Cheltenham | Water /Flood Risk | Construction | Essential | s.106 / Service provider | Y | Y | N | N | 2475000 | 2475000 | Gloucestershire County Council | Construction | Operational |  | This is a Gloucestershire County Council led scheme to reduce the risk of surface water flooding from the Cotswold Escarpment to 213 properties in Whaddon, Lynworth and Prestbury. The scheme includes channel diversions into two flood storage areas during high flows and Property Level Resilience measures. | No
Aldney Island Improvements, River Severn | Water /Flood Risk | Feasibility | Essential | s.106 / Service provider | Y | N | N | N | Unknown | 0 | Environment Agency |  | Construction | Operational | Identified within the FCERM Current Investment Programme. | Yes
Gloucester Screens Rationalisation | Water / Flood Risk | Feasibility | Desirable | s.106 / Service provider | Y | N | N | N | Unknown | 0 | Environment Agency |  | Construction | Operational | Identified within the FCERM Current Investment Programme. | Yes
SUDs retrofitting, Gloucester City Centre | Water / Flood Risk | Feasibility | Essential | s.106 / Service provider | Y | N | N | N | Unknown | 0 | Environment Agency |  | Construction | Operational | Identified within the FCERM Current Investment Programme. ESIF funding identified. | Yes
River Severn Property Level Protection, Gloucester to Tewkesbury | Water / Flood Risk | Feasibility | Essential | s.106 / Service provider | Y | N | N | N | Unknown | 0 | Environment Agency |  | Construction | Operational | Identified within the FCERM Current Investment Programme. | Yes
Leisure@ Cheltenham Refurbishment | Community | Completed | Desirable | Service provider | Y | Y | N | N | 2500000 | 2500000 | Sport England / Cheltenham Borough Council | Construction | Operational |  | Refurbishment of Leisure@Cheltenham is expected to cost £2.5million, of which £330,000 has been provided by Sport England (specifically designated to swimming facilities). Works began in March 2018 and were due for completion in summer 2018 | No
Blackbridge Sports and Community Hub | Community | Planning | Desirable | Service provider | Y | Y | N | N | Unknown | Unknown | Active Gloucester | Construction | Operational |  | Consultation on the proposed new community sports hub at Blackbridge Playing Fields was undertaken in March 2020 with a view to submitting a planning application in late 2020. | No

## Sheet2 (hidden)
Project Type | Project Status | Project Priority Level | Contribution Type | Feasibility Undertaken? | Alternative / Match Funding Identified? | Statutory undertaker remit? | Linked to SA? | Estimated / Agreed Cost | Lead Organisation
Transport | Feasibility | Critical | s.106 | Y | Y | WPD | Winneycroft
Education | Planning | Essential | CIL | N | N | SSE | W. Chelt
Healthcare | Construction | Desirable | Capital Ex |  |  | WWU | Twigworth
Community | Completed |  | Developer delivery |  |  | Bristol Water | Fiddington
Water /Flood Risk |  |  | Service provider |  |  | Severn-Trent Water | Mitton
GI |  |  | Land/Property |  |  | Thames Water | Innsworth
[6 empty] | Wessex Water | N Churchdown
[6 empty] | N/A | S Churchdown
N Brockworth
NW Chelt
Leckhampton
MOD Ashchurch
Ashchurch
N

## Sources
List of data sources accessed July 2020 | Link
Gloucestershire Economic Growth Capital Investment Pipeline (CIP) | https://www.gloucestershire.gov.uk/business-property-and-economy/gloucestershire-economic-growth-capital-investment-pipeline-cip/
Gloucestershire County Council Highways Major Projects | https://www.gloucestershire.gov.uk/highways/major-projects-list
Highways England Road Investment Strategy 2
M5 Junction 10 news | https://www.gloucestershire.gov.uk/gloucestershire-county-council-news/news-june-2020/junction-10-upgrade-moving-forward/
West Cheltenham Transport Improvement Scheme | https://www.gloucestershire.gov.uk/gloucestershire-county-council-news/news-june-2020/its-official-16million-cycling-and-walking-work-coming-to-west-cheltenham/
Leckhampton School | https://www.gloucestershire.gov.uk/gloucestershire-county-council-news/news-may-2020/plans-for-new-cheltenham-school-to-be-considered/
Gloucestershire’s Local Transport Plan (2015-2041) Draft Plan
Gloucester School Places | https://www.gloucestershire.gov.uk/education-and-learning/school-planning-and-projects/gloucester-school-places/
Primary Care Infrastructure Plan 2016 to 2026